| Tasks | Estimated completion date or time | Status Update |
| --- | --- | --- |
| 1) Order reagents, peptide substrate etc. except radioactive NAM | 4 days | Done |
| 2) Transfer HPLC to radioactive room, assemble fraction collector, reprogram the fraction collector, and test the HPLC for proper functioning. | 2 weeks | Done |
| 3) Test the HPLC, performance of column with non-radioactive compounds (NAD, NAM, different peptides); get the idea of different peaks and concentration relationship, retention time etc. | 1-2 weeks |  |
| 4a) Order radioactive C14-NAM 4b) Calibrate scintillation counter with radioactive material | 1-2 weeks | 4a- Done |
| 5) Purify protein for pilot experiment, characterization of purified protein. | 1-2 weeks | Sudipto will take over |
| 6a) Assay development, standardization, and data analysis 6b) Run in-house Sirt3 (10 and 20 uL) on the column 6c) Run buffer, blank run 6d) Run 3 reactions with in-house enzyme with different conc of peptide | 4-6 weeks This section (6b-e) will be completed by 2/8/2016 | 6a-mostly done 6b-e completed (on time) |
| 7) Dose response curve for DHP2c 7a) in assay buffer with in-house enzyme [DHP2c]: 0, 10, 25, 50, 75, 100 uM [NAD]: 1.5 mM, Enzo peptide: 100 uM Total 8 reactions (including Buffer and Blank) 7b) in 1% DMSO with in-house enzyme Run buffer and blank with 1% DMSO [DHP2c]: 0.5, 1, 2 mM Total 5 reactions | 7a) complete by 2/11/2016 7b-c) complete by 2/16/2016 |  |
| 8) Dose response assay with p53 peptide 8a) run 500, 1000, 1500, 2000, 3000 pmoles acetylated p53 peptide 8b) run 500, 1000, 1500, 2000, 3000 pmoles deacetylated p53 peptide I will choose only three concentrations of each. 8c) with DHP2c in assay buffer [DHP2c]: 0, 10, 25, 50, 75, 100 uM [NAD]: 1.5 mM, p53 peptide: 100 uM (find out what concentration is suitable) Total 8 reactions (including Buffer and Blank) | 8a-b) complete by 2/17/2016 8c) complete by 2/23/2016 |  |
| 9) Initial rate kinetics with in-house Sirt3 and Enzo peptide 9a) without DHP2c Six different concentrations of NAD+ (50, 100, 200, 400, 600, 1200 uM) Five different time points (to be decided with previous experience) Total 30 reactions. 9b) with 25 uM DHP2c Six different concentrations of NAD+ (50, 100, 200, 400, 600, 1200 uM) with 25 uM DHP2c in each. Five different time points (same time points as in 9a) Total 30 reactions. | 9a) completed by 3/3/2016 9b) completed by 3/14/2016 |  |