| Tasks | Estimated completion date or time | Status Update |
| --- | --- | --- |
| 1) Order reagents, peptide substrate etc. except radioactive NAM | 4 days | Done |
| 2) Transfer HPLC to radioactive room, assemble fraction collector, reprogram the fraction collector, and test the HPLC for proper functioning. | 2 weeks | Done |
| 3) Test the HPLC, performance of column with non-radioactive compounds (NAD, NAM, different peptides); get the idea of different peaks and concentration relationship, retention time etc. | 1-2 weeks |  |
| 4a) Order radioactive C14-NAM 4b) Calibrate scintillation counter with radioactive material | 1-2 weeks | 4a- Done |
| 5) Purify protein for pilot experiment, characterization of purified protein. | 1-2 weeks | Sudipto will take over |
| 6) Assay development, standardization, and data analysis | 4-6 weeks |  |
| 7a) Based on #5, we decide how much protein needed to complete a assay, modify assay to include inhibitors, activators 7b) Once we complete #6, we will be ready to calculate k5 (base exchange constant) in a reaction. The limiting factor will be HPLC run. For example, to calculate k5, we will use 13 [NAM]C14 concentrations and each will have 5 different time points, thus we will run 65 sample (for one set of reaction) to run on HPLC. | 7-8 weeks (May change) |  |