| Tasks | Estimated completion date or time | Status Update |
| --- | --- | --- |
| 1) Order reagents, peptide substrate etc. except radioactive NAM | 4 days | Done |
| 2) Transfer HPLC to radioactive room, assemble fraction collector, reprogram the fraction collector, and test the HPLC for proper functioning. | 2 weeks |  |
| 3) Test the HPLC, performance of column with non-radioactive compounds (NAD, NAM, different peptides); get the idea of different peaks and concentration relationship, retention time etc. | 2 weeks |  |
| 4a) Order radioactive C14-NAM 4b) Calibrate scintillation counter with radioactive material | 1-2 weeks |  |
| 5) Purify protein for pilot experiment, characterization of purified protein. | 6 days |  |
| 6) Assay development, standardization, and data analysis | 3-4 weeks |  |
| 7a) Based on #5, we decide how much protein needed to complete a assay, modify assay to include inhibitors, activators 7b) We need input on what kind of assay modification we will be doing. How many inhibitors/activators we will be testing. This will help me to decide how much protein I will need to complete the assay. | TBD |  |

Protocol: This was published for Sir2

Reaction mix

50 mM Potassium Phosphate pH 7.8

300 uM peptide

600 uM NAD+

[carbonyl-14C]-nicotinamide (varying concentration 0-1200 uM)

1 uM Enzyme

The reaction will be started by addition of enzyme. Total reaction time is 2 hours. 10 uL reaction mix will be take out at 0, 30, 60, 90, and 120 min and quenched with 50 uL of 50 mM ammonium acetate (pH 5.0) and run on HPLC.