| Schedule revised (8-3-2016): 1: Start date is pending approval of this schedule; 2: Minimum amount of in-house Sirt3 needed 3120 uL (3500 ul) of 1.5U/ul. I want to have some extra Sirt3 at my disposal, just in case I need it during this period. 3: All inter-day repeats. |  |  |
| --- | --- | --- |
| Task | Expected completion date | Remarks/Status |
| PMC-AU1: Determine detectability limit for c-K122-MnSOD peptide (Total: 20 samples) - 0.625, 1.25, 2.5, 5, 10 uM of Non-Ac-K122 (5 samples) - Repeat one time (with same sample; intra-day) (5 samples) - Run #a from fresh sample (5 samples) - Repeat one time #c (5 samples) | Completed by 08-12-16 One HPLC | AU46 |
| PMC-AU2: Estimate saturating [NAD] Total: 30 samples - Three reactions with 1, 2, and 3 mM NAD and 600 uM K122-MnSOD, 5U/rxn, 30 min (6 samples) - One repeat #a (6 samples) - Saturating [NAD] (from #a), 5% DMSO) + [peptide] (from PMC-AU1) to see if other components affect the detection limit. Time: 5 and 30 min, 5U and 10U/Rxn (6 samples) - 2x Repeat #c (12 samples) | Completed by 08-16-2016 One HPLC, [a, b: duplicate, c,d: triplicate] | AU47 In-house Enzyme: 30 x 10U = 300U Stock: 1.5U/ul Needed: 200 uL |
| PMC-AU3: See the minimum [NAD], and saturating Peptide (600 uM) can be used (endpoint, 30 min, 60 min). All reactions should be done in 5% DMSO (Total 12 samples) - 50 uM NAD, 600 uM K122-MnSOD (2 samples) - 75 uM NAD, 600 uM K122-MnSOD (2 samples) - 100 uM NAD, 600 uM K122-MnSOD (2 samples) - One time repeat (6 samples) | Completed by 08-19-2016 One HPLC, Duplicate | AU48 In-house Enzyme: 12 x 10U = 120U Stock: 1.5U/ul Needed: 80 uL |
| PMC-AU4: HNK dose response, [HNK] = 0, 1, 5, 10, 25, 50, 100, 200 uM, Time = TBD (48 Samples) - Minimum [NAD], and 600 uM K122 (8 samples) - Saturating [NAD] , minimum K122 (8 samples) - Two time repeat of each 1 and 2 (32 samples) | Completed by 08-30-2016 One HPLC, Triplicate | AU49 In-house Enzyme: 48 x 10U = 480U Stock: 1.5U/ul Needed: 320 uL |
| PMC-AU5: Determine Km NAD with and w/o 5% DMSO, with Honokiol (378 samples): - Saturating K-122 MnSOD (600 uM), [NAD] = 100, 200, 400, 600, 800, 1200, 2000 uM (May add 1 more [NAD] based on minimum [NAD] sufficient to drive the reaction. Time: 5, 10, 20, 40, 80, 120 min (42 samples) - Same reactions with 5% DMSO (42 samples) - Same reactions with one [Honokiol] in 5% DMSO (42 samples) - Two repeats (1,2,3) above to confirm (252 samples) | Completed by 10-05-2016 Three HPLC, Triplicate | AU50 In-house Enzyme: 378 x 10U = 3780U Stock: 1.5U/ul Needed: 2520 uL |

Footnote:

- For duplication, two HPLC will be used and the completion date is 10.3.2016. As suggested triplicate will be done either in house at later time or by CRO. Since the duplication/ triplication will be run parallel on the 2nd/3rd HPLC, the total time will not be reduced significantly.

- In the revised AU/XG schedules, there is no conflict of usage of HPLC. AU will use one HPLC for expt. PMC-AU4, which aligned to XG’s.

- Experiment AU2 a, b, are for saturating NAD determination. And c, d is to see if selected condition gives quantifiable product with saturating [NAD] and minimum peptide conc chosen.